## Roadmap
Aim-Truth Rig — 16-Week Phased Roadmap
Week 1 = w/c 2026-08-03. Effort in solo-days. Update the Status column; % complete rolls up on the Dashboard.
Wk | Week of | Phase | Work item | Deliverable / exit criterion | Depends on | Effort (days) | Status | Risk link
1 | 2026-08-03 | P0 Observability | Archaeology spike on inherited stack (timebox 4 days) | Written one-pager: detector, filter type + rate, latency scheme, gimbal protocol. Explicit decision: instrument vs. replace tracker. | — | 4 | Not started | R2
1 | 2026-08-03 | P0 Observability | Confirm camera model + trigger/strobe capability (Q1) | Datasheet line confirming external trigger in OR strobe out. GO/NO-GO on full spin range. | — | 0.5 | Not started | R1
1 | 2026-08-03 | P0 Observability | Confirm compute headroom + disk throughput for full-rate logging (Q4) | Measured write bandwidth vs. required frame+state rate. No dropped frames under load. | — | 0.5 | Not started | R2
2 | 2026-08-10 | P0 Observability | Structured estimator-state logging (REQ-0.1) | Every filter update logged, not just final aim output. Self-describing dataset format w/ metadata. | Wk1 spike | 3 | Not started | —
2 | 2026-08-10 | P0 Observability | Gimbal commanded-vs-actual angle logging (REQ-0.2) | Second channel on same time base. Enables estimator-vs-servo error split. | REQ-0.1 | 1 | Not started | —
2 | 2026-08-10 | P0 Observability | Order long-lead parts (motor if not owned, MCU, frame) | Parts ordered. Piezo parts deliberately NOT ordered yet. | Q1 answered | 0.5 | Not started | R5
3 | 2026-08-17 | P0 Observability | Hardware frame trigger / strobe capture (REQ-0.3) | MCU drives or captures camera exposure; encoder latched in same ISR. | Parts | 3 | Not started | R1
3 | 2026-08-17 | P0 Observability | LED sync verification test | Measured sync error written into dataset metadata. MUST be <= 200 us. | REQ-0.3 | 1.5 | Not started | R1
3 | 2026-08-17 | GATE | WEEK 3 HARD GATE — sync error <= 200 us? | If > 1 ms with no hardware path: descope to static-target check, abandon spinning rig. | LED test | 0 | Not started | R1
4 | 2026-08-24 | P1 Estimator | Build spin rig: frame, hub, plate mount (REQ-1.1) | Direct-drive GM6020 mount. Static / constant-speed / step-change modes. Speed held to 2%. | Wk3 gate | 4 | Not started | R7
4 | 2026-08-24 | P1 Estimator | Safety: guard, hardware E-stop, captive fasteners | E-stop cuts motor power in hardware, not software. Verified by test. | Frame | 1 | Not started | SAFETY
5 | 2026-08-31 | P1 Estimator | Encoder truth pipeline at >=1 kHz, <=0.05 deg (REQ-1.2) | Absolute plate angle on rig time base. Validated against high-fps phone video. | Rig built | 2 | Not started | R8
5 | 2026-08-31 | P1 Estimator | Analysis: bias / latency / noise decomposition (REQ-1.3) | Signed error vs. time + 3 scalars per spin rate. Latency via cross-correlation lag. | Encoder truth | 3 | Not started | —
6 | 2026-09-07 | P1 Estimator | Estimator-vs-servo error split (REQ-1.4) | Same analysis on gimbal feedback channel. Error budget attributed. | REQ-1.3 | 1.5 | Not started | —
6 | 2026-09-07 | P1 Estimator | Baseline report at 0.5 / 1.5 / 3.0 rev/s | One-page report. This is the Week 6 baseline that M5 is measured against. | REQ-1.4 | 1.5 | Not started | —
6 | 2026-09-07 | GATE | WEEK 6 PAYBACK GATE — did rig data change a decision? | If no tuning decision was made on rig data: PARK until off-season. | Baseline | 0 | Not started | R3
7 | 2026-09-14 | P4 Replay | Deterministic replay harness (REQ-4.1) | Dataset in + params in -> error metrics out. Bit-for-bit reproducible across runs. | Wk6 gate | 4 | Not started | —
7 | 2026-09-14 | P2 Live-fire | Confirm firing space + referee set availability (Q2, Q3) | Booked space at fixed range; referee set confirmed or Phase 2 goes paper-only. | — | 0.5 | Not started | R4
8 | 2026-09-21 | P4 Replay | Parameter sweep driver + scalar cost function (REQ-4.2) | Grid/random search ranking configs. Runs in seconds, no hardware. | REQ-4.1 | 2.5 | Not started | —
8 | 2026-09-21 | P2 Live-fire | NOISE FLOOR: static plate, clamped launcher, witness paper (REQ-2.1) | Group spread of the launcher alone. Hard floor on achievable accuracy. Do this BEFORE any hit-rate number. | Space | 1.5 | Not started | —
8 | 2026-09-21 | P2 Live-fire | Per-shot muzzle velocity logging (REQ-2.2) | Velocity joined to time-of-flight and required lead angle. | Referee link | 1 | Not started | R4
9 | 2026-09-28 | P2 Live-fire | Hit rate + group offset vs. spin rate (REQ-2.3) | Chart with dispersion floor drawn as horizontal reference. Witness paper digitised per magazine. | REQ-2.1 | 3 | Not started | —
9 | 2026-09-28 | P4 Replay | Held-out validation split (REQ-4.3) | Tune on set A, report on set B. Guards against dataset memorisation. | REQ-4.2 | 1.5 | Not started | R6
10 | 2026-10-05 | P3 Piezo | GO/NO-GO BENCH TEST: 4 piezos, spare plate, grid of taps (REQ-3.1) | Calibrated RMS error on a known grid. NO-GO if > 25 mm -> reallocate to P4. | Wk9 | 3 | Not started | R5
10 | 2026-10-05 | GATE | WEEK 10 PHASE-3 GATE + M4 adoption check | Piezo <= 25 mm RMS? AND >= 3 tuning decisions made on rig data? | Bench test | 0 | Not started | R5
11 | 2026-10-12 | P3 Piezo | Comparator front end + STM32 input-capture timing | 4-channel threshold crossings timestamped on rig time base. ns-class resolution. | Wk10 gate | 3 | Not started | —
12 | 2026-10-19 | P3 Piezo | Multilateration + empirical calibration map (REQ-3.2) | Grid-derived map, NOT an analytical wave-speed model. Stored with rig config. | Front end | 4 | Not started | —
13 | 2026-10-26 | P3 Piezo | Integrate onto live plate; join impacts to estimator state (REQ-3.3) | Each impact carries rig timestamp; paired with estimator state at firing minus TOF. | Calibration | 3 | Not started | —
13 | 2026-10-26 | P4 Replay | Real-robot validation of swept parameters (REQ-4.4) | No offline-selected parameter adopted without live validation. | REQ-4.3 | 2 | Not started | R6
14 | 2026-11-02 | P3 Piezo | Accuracy acceptance: <=25 mm RMS, >=95% quadrant (M7) | Measured on held-out grid positions, not calibration positions. | Integration | 2 | Not started | R5
14 | 2026-11-02 | P1 Estimator | M5 re-measurement vs. Week 6 baseline | Same rig, same protocol. Target: >= 30% estimator error reduction. | P4 tuning | 1.5 | Not started | —
15 | 2026-11-09 | Consolidate | Regenerate every reported number from stored datasets | Single command per figure. No number that exists only in a screenshot. | All | 2 | Not started | —
15 | 2026-11-09 | Consolidate | Dataset archive + metadata audit | Every recording labelled with rig config, sync error, camera settings, git commit. | All | 1.5 | Not started | —
16 | 2026-11-16 | Consolidate | Final report: error budget, tuning outcomes, known limits | Includes an honest section on what the rig does NOT measure (see PRD R6). | Wk15 | 2.5 | Not started | R6
16 | 2026-11-16 | Consolidate | Off-season backlog: what v2 should do differently | Written while the pain is fresh. | — | 1 | Not started | —
TOTAL EFFORT (solo-days)
[5 empty] | Available (16 wks x 2.5 days/wk realistic solo, in-season) | 40
Headroom (negative = overcommitted)
Blue = your input. Adjust available days to your real capacity.
CAPACITY REALITY CHECK: the plan as scoped is ~66.5 solo-days against ~40 available at 2.5 days/week. Dropping Phase 3 entirely (15 days) still leaves ~51.5.
Closing the gap needs one of: (a) ~3.3 days/week instead of 2.5, (b) drop Phase 3 AND cut Phase 2 to a single dispersion-floor session, or (c) extend to 20 weeks.
This is deliberate. A plan that fits perfectly on day one has not been costed honestly. Decide which lever to pull at the Week 6 payback gate, when there is evidence.

## Dashboard
Dashboard
All figures are formulas over the Roadmap and Risks tabs — they update as you edit Status.
PROGRESS
Total work items
Done
In progress
Blocked
Descoped
% complete
EFFORT BY PHASE (solo-days)
Phase | Planned | Done | % done
P0 Observability
P1 Estimator
P2 Live-fire
P3 Piezo
P4 Replay
Consolidate
TOTAL
GATES — the decisions that keep this project honest
Gate | Week | Test | Action on failure
Sync gate | 3 | Measured camera-to-encoder sync error <= 200 us | If > 1 ms with no hardware path: descope to static-target check, abandon spinning rig
Payback gate | 6 | Has rig data changed at least one tuning decision? | Park the project until off-season; robot work wins during the season
Phase 3 gate | 10 | Piezo bench RMS <= 25 mm on a known grid | Do not integrate. Reallocate the 4 weeks to Phase 4 replay tuning
Adoption gate | 10 | >= 3 tuning decisions made on rig data (M4) | The tool is not being used. Stop building; find out why
Drift tripwire | any | 2 consecutive weeks with no dataset recorded | You are building infrastructure for its own sake. Record something crude, re-plan

## BOM
Bill of Materials
Blue = your input (adjust qty/price to what you actually pay or already own). Budget ceiling from kickoff: $500.
Item | Purpose | Phase | Qty | Unit $ | Line $ | Already own? | Order by
GM6020 gimbal motor | Direct-drive spin + absolute encoder ground truth (0.044 deg, no backlash) | P1 | 1 | 110 |  | Likely | Wk 2
STM32F4 dev board | Rig time base, CAN, camera trigger, piezo input capture | P0 | 1 | 15 |  | Maybe | Wk 2
USB-CAN adapter | Motor command + host link | P1 | 1 | 25 |  | Likely | Wk 2
24 V PSU | Motor supply (or reuse a team battery) | P1 | 1 | 25 |  | Maybe | Wk 2
Aluminium extrusion + base plate + fasteners | Rigid frame; must not walk under vibration (risk R7) | P1 | 1 | 60 |  | No | Wk 2
3D-printed hub + sensor mounts | Interface to standard armor plate; captive fasteners | P1 | 1 | 8 |  | In-house | Wk 3
Opto-isolator + wiring + connectors | Camera trigger isolation | P0 | 1 | 12 |  | No | Wk 2
LED + driver | Sync verification test (REQ-0.3) | P0 | 1 | 8 |  | No | Wk 2
Carbon / witness paper | Phase 2 spatial ground truth. Best value per dollar in this BOM. | P2 | 1 | 5 |  | No | Wk 7
Piezo discs | Impact localisation elements | P3 | 4 | 2 |  | No | Wk 10*
Comparator + analogue front end parts | Threshold crossing detection for TDOA | P3 | 1 | 27 |  | No | Wk 10*
Safety guard / polycarbonate shield | Spinning plate containment + eye protection zone | P1 | 1 | 30 |  | No | Wk 4
SUBTOTAL (all phases)
Less items likely already owned
Less Phase 3 (gated at Wk 10)
COMMITTED SPEND BEFORE WK 10
|  |  |  | Budget ceiling | 500
Headroom vs. worst case (buy everything)
* Do not order Phase 3 parts until the Week 10 go/no-go bench test passes. Ordering early converts a reversible decision into a sunk cost.
Assumption: GM6020 and USB-CAN adapter marked 'Likely' owned — confirm against the team's spares inventory in Week 1.

## Risks
Risk Register
Score = Impact x Likelihood (1-5 each). Review at every gate. Blue cells are your scoring inputs.
ID | Risk | Impact (1-5) | Likelihood (1-5) | Score | Severity | Mitigation | Owner | Review at
R1 | Time sync cannot reach +/-200 us (camera lacks trigger/strobe line) | 5 | 3 |  |  | Confirm camera trigger capability in Week 1 before any other purchase. Fallback: cap spin rate at ~1 rev/s so the artefact stays below the signal, and state the reduced range in every report. | Self | Wk 3 gate
R2 | Inherited stack undocumented, unbuildable, or unloggable | 4 | 4 |  |  | Timeboxed 4-day archaeology spike ending in a written decision: instrument it, or replace the tracker with a minimal known-good one. Do not drift into an open-ended refactor. | Self | Wk 1
R3 | Solo builder + live season -> project starved of time | 4 | 4 |  |  | Every phase gate delivers standalone value. Week 6 payback gate. Prefer a finished Phase 1 over a half-finished Phase 3. | Self | Wk 6 gate
R4 | No spare referee system available for the target rig | 2 | 3 |  |  | Witness paper covers spatial measurement independently, so referee counting is optional not blocking. Confirm availability by Week 6 (Q2). | Self | Wk 7
R5 | Piezo localisation misses the 25 mm accuracy target | 3 | 3 |  |  | Week 10 bench go/no-go on a spare plate before any integration or full parts order. Reallocate to Phase 4 on a no-go. | Self | Wk 10 gate
R6 | Overfitting to the rig: tuned params help on the bench, hurt on a real robot | 5 | 4 |  |  | The rig measures a proxy, not the goal. Mandate real-robot validation before adopting any tuned parameter (REQ-4.4). Keep held-out datasets (REQ-4.3). Vary lighting, range and background between recordings. | Self | Wk 13
R7 | Frame resonance or walk corrupts encoder truth at high spin | 3 | 2 |  |  | Sweep spin rate looking for anomalous encoder residuals. Ballast or clamp the frame. Record a static-plate control run every session. | Self | Wk 5
R8 | Rig ground truth trusted without independent validation | 4 | 3 |  |  | Film the plate with a phone at high frame rate and confirm the encoder-reported rate matches. Cheap, and it catches whole classes of wiring and unit errors. | Self | Wk 5
R9 | Injury from spinning plate or projectile | 5 | 2 |  |  | Hardware E-stop cutting motor power (not software). Mechanical guard. Captive fasteners on the hub. Eye protection whenever the launcher is armed. Non-negotiable. | Self | Wk 4
R10 | Logging drops frames under load, biasing datasets toward easy scenes | 4 | 3 |  |  | Measure disk throughput and CPU headroom in Week 1 (Q4). Assert on dropped-frame counters and fail loudly rather than silently. | Self | Wk 2
Highest score:
Severity thresholds: Critical >=15, High >=9, Medium >=4, Low <4.

## Metrics
Success Metrics
Blue cells are yours to fill in as measurements land. Status computes automatically where a target is numeric.
ID | Metric | Target | Actual | Due | Status | How measured
M1 | Ground-truth uncertainty at 3 rev/s | <= 0.25 deg |  | Wk 3 | Pending | LED sync test + encoder spec, recorded in dataset metadata
M2 | Estimator error characterised | Bias, latency, noise at 3 spin rates |  | Wk 6 | Pending | Phase 1 report; latency by cross-correlation lag
M3 | Tuning cycle time | <= 10 min, param change to number |  | Wk 8 | Pending | Stopwatch over 5 trials
M4 | Real adoption | >= 3 tuning decisions on rig data |  | Wk 10 | Pending | Decision log. THE metric that matters most.
M5 | Measured improvement | >= 30% error reduction vs. Wk 6 baseline |  | Wk 14 | Pending | Same rig, same protocol, re-measured
M6 | Live-fire baseline | Hit rate vs. spin rate, with dispersion floor |  | Wk 9 | Pending | Phase 2 chart from witness paper + referee counts
M7 | Impact localisation (if P3 proceeds) | <= 25 mm RMS, >= 95% quadrant |  | Wk 14 | Pending | Held-out grid positions, not calibration positions

## Open Questions
Open Questions
Q1 and Q4 gate Week 1 and should be answered before anything is ordered.
ID | Question | Blocks | Needed by | Status | Answer
Q1 | What camera does the aimbot use, and does it expose an external trigger input or a strobe output? | REQ-0.3, the whole time-base design, and the usable spin-rate range | Wk 1 | Open
Q4 | What compute runs the aimbot, and does it have spare CPU and disk throughput for full-rate logging? | REQ-0.1 - logging that drops frames under load produces biased datasets | Wk 1 | Open
Q5 | Which armor plate size is the reference target: small (~135 mm) or large (~235 mm)? | Hub design, piezo geometry, calibration grid | Wk 2 | Open
Q2 | Is a spare referee system set available to mount on the target rig? | Phase 2 hit counting (not spatial measurement, which paper covers) | Wk 6 | Open
Q3 | Is there a space where the launcher can be fired safely and repeatedly at a fixed range? | All of Phase 2; may force a shorter test range | Wk 6 | Open
Q6 | Will anyone else on the team use this, even informally? | Whether any documentation effort is justified at all | Wk 8 | Open
Legend: blue cells are for you to fill in. Answer Q1 before ordering anything - it determines whether the project's core premise holds.

## Sync Budget
Time-Base Error Budget
The calculation behind the project's hardest requirement. Blue cells are inputs - change them to test your own setup.
INPUTS
Max target spin rate (rev/s) | 3
Assumed clock skew, software timestamps (ms) | 2
Assumed clock skew, hardware trigger (ms) | 0.05
Encoder counts per revolution (GM6020) | 8192
Smallest aiming error we want to resolve (deg) | 0.5
DERIVED
Angular velocity at max spin (deg/s)
Apparent error from software timestamps (deg)
Apparent error from hardware trigger (deg)
Encoder quantisation (deg)
Combined hardware-path uncertainty (deg, RSS)
Software path as % of the signal we want to resolve
Hardware path as % of the signal we want to resolve
VERDICT
SENSITIVITY: apparent angular error (deg) by spin rate and clock skew
Spin rate (rev/s) \ Clock skew (ms) | 0.05 | 0.2 | 1 | 2 | 5
0.5
1
1.5
2
3
Red = the measurement artefact exceeds the 0.5 deg error you are trying to detect. Green = comfortably below it.
Source of encoder spec: DJI GM6020 absolute encoder, 8192 counts/rev. All other values are inputs you can change.