## Roadmap
Portable Aimbot Target - 26-Week Roadmap
Week 1 = w/c 2026-08-03. Phase 1 ships a usable workshop target by Week 6. Update Status; the Dashboard rolls up.
Wk | Week of | Phase | Work item | Deliverable / exit criterion | Depends on | Days | Status | Risk
1 | 2026-08-03 | 1 Workshop target | Freeze head-to-base interface spec (REQ-M6) | Bolt/slot pattern, vertical datum, single 24V+data connector. Written down and treated as frozen. | - | 2 | Not started | -
1 | 2026-08-03 | 1 Workshop target | Define transport envelope + weight budget baseline | Case shape candidates costed; every head part gets a max-dimension and mass allocation before it is designed. | - | 1.5 | Not started | R3
1 | 2026-08-03 | 1 Workshop target | Confirm fabrication access (Q7) | 3D printer / machining / hand-cut only. Sets realistic effort for every mechanical part. | - | 0.5 | Not started | -
2 | 2026-08-10 | 1 Workshop target | Head hub + arm design, inertia budgeted (REQ-M1, M2) | Head inertia estimated BEFORE build; plate radius minimised (inertia scales with r^2). | Interface | 4 | Not started | R9
2 | 2026-08-10 | 1 Workshop target | Workshop base - deliberately crude, heavy, ballasted (REQ-M7) | Steel plate and ballast. No design effort spent here on purpose. | Interface | 1 | Not started | -
3 | 2026-08-17 | 1 Workshop target | Fabricate head; route wiring through GM6020 hollow shaft (REQ-M4) | Head assembled. 18mm hollow shaft carries power/data on the rotation axis. | Design | 4 | Not started | -
3 | 2026-08-17 | 1 Workshop target | Joint design pass: locate vs. clamp on every joint (REQ-M10..M13) | Every structural joint has a locating feature AND a separate preload element. All fasteners captive. | Head | 2 | Not started | R1
4 | 2026-08-24 | 1 Workshop target | Motor control: 0.25-3.0 rev/s, speed hold within 2% (REQ-M2) | Commanded vs. actual logged. Static hold mode works. Spin-up time measured. | Head | 3 | Not started | R9
4 | 2026-08-24 | 1 Workshop target | Safety: hardware E-stop, balance verification, guarding (R11) | E-stop cuts motor power in HARDWARE. Balance checked before first full-speed run. | Motor ctrl | 1.5 | Not started | R10
5 | 2026-08-31 | 1 Workshop target | Endurance session + full joint re-check (R1) | Run at full speed for a realistic session, then inspect every joint. Loose joints found NOW, not in month 5. | Safety | 1.5 | Not started | R1
5 | 2026-08-31 | 1 Workshop target | Weigh every head part against the budget | Actual masses replace estimates in the Weight Budget tab. | Head | 0.5 | Not started | R3
6 | 2026-09-07 | 1 Workshop target | Phase 1 acceptance: a TEAMMATE runs a full session unaided (M2) | Someone who did not build it sets up and practises without asking how. Tests the design, not your memory. | Endurance | 1 | Not started | R5
6 | 2026-09-07 | GATE | WEEK 6 ADOPTION GATE - does a teammate reach for it unprompted? | If not, understand why before adding rail, sensors or a suitcase to it. | Session | 0 | Not started | R5
5 | 2026-08-31 | 2 Rail | Rail spec: length, mounting, workshop constraints (Q5) | Confirmed against the actual space. Belt drive, stationary motor at one end (REQ-M8). | - | 1 | Not started | -
7 | 2026-09-14 | 2 Rail | Build rail: extrusion, V-wheel carriage, belt drive | Carriage runs smoothly full length. Limit switches fitted. | Rail spec | 4 | Not started | -
8 | 2026-09-21 | 2 Rail | Carriage mounts head via the frozen interface | Head bolts on with no rework. Proves the interface spec was right. | Rail, Interface | 1 | Not started | -
9 | 2026-09-28 | 2 Rail | Unified control: translation + spin together | One interface commands both axes. Repeatable motion patterns. | Carriage | 3 | Not started | -
10 | 2026-10-05 | 2 Rail | Rail acceptance: reliable over a full session | No jams, no belt skip, no limit-switch faults across a practice session. | Control | 1 | Not started | -
8 | 2026-09-21 | 3 Plates + UI | ONE prototype instrumented plate (REQ-E5) | Single plate, 4 piezos, comparator front end. Built to learn, not to ship. | Wk6 gate | 4 | Not started | R4
9 | 2026-09-28 | 3 Plates + UI | Bench characterisation against a tap grid (REQ-E4) | Empirical calibration map. Measured RMS error on HELD-OUT grid positions. | Prototype | 3 | Not started | R4
10 | 2026-10-05 | GATE | WEEK 10 PLATE GATE - RMS <= 25mm on the prototype? | If no: do not build four. Ship with stock plates + referee counting, which is still a good training tool. | Bench test | 0 | Not started | R4
11 | 2026-10-12 | 3 Plates + UI | Rotating-frame electronics: head MCU + slip ring (REQ-E1..E3) | Only digital events cross the interface. Slip ring carries 24V + digital, ~4 conductors not 16+. | Wk10 gate | 4 | Not started | R11
12 | 2026-10-19 | 3 Plates + UI | Build remaining 3 plates; per-plate calibration | All four calibrated and characterised. Replaceable impact faces fitted (REQ-M14). | Electronics | 4 | Not started | R4
13 | 2026-10-26 | 3 Plates + UI | Boot self-test: 16 channels, motor, encoder, referee (REQ-E6) | Power-up health check. This is what makes the machine trustworthy. | Plates | 2.5 | Not started | R4
14 | 2026-11-02 | 3 Plates + UI | Web UI: Live + Health screens | Spin rate, speed control, live impacts on 4 plate outlines, green/red health per item. | Self-test | 4 | Not started | -
15 | 2026-11-09 | 3 Plates + UI | Web UI: Session + History + CSV export | Hit distribution, group centre and spread, session comparison. | UI core | 3 | Not started | -
16 | 2026-11-16 | 3 Plates + UI | Referee cross-check in the workshop (REQ-E7) | Custom plate hit count vs. referee count. Agreement validates both. | UI | 2 | Not started | R12
17 | 2026-11-23 | 3 Plates + UI | Phase 3 acceptance: 25mm RMS all plates, UI usable unaided | A teammate uses the UI without explanation. | All P3 | 1.5 | Not started | -
14 | 2026-11-02 | 4 Travel kit | Travel stand concept + packing study | Stand design against the FROZEN head geometry. Longest irreducible part identified. | Head final | 3 | Not started | R6
16 | 2026-11-16 | 4 Travel kit | Choose case shape from the largest irreducible part (S7.1) | Case proportions selected AFTER the part list, not before. Least wasted volume. | Packing study | 1 | Not started | R3
18 | 2026-11-30 | 4 Travel kit | Build travel stand: tool-free, packs flat, on-site ballast (REQ-M9) | Assembles without tools. Stable at 3 rev/s on a smooth floor. | Concept | 5 | Not started | R6
20 | 2026-12-14 | 4 Travel kit | Custom case + cut foam, pocket per part (REQ-M14, M15) | Empty pocket = visible missing part. Assembly order printed inside the lid. | Stand | 4 | Not started | R8
21 | 2026-12-21 | GATE | WEEK 20-21 PACKING TEST - under 23kg and 158cm? | If not, decide deliberately: oversize fee, freight, or workshop-only. Not at the check-in desk. | Case | 0 | Not started | R3
22 | 2026-12-28 | 4 Travel kit | Drop test representative of baggage handling (REQ-M16) | Head and plates survive. Failures found at home, not in China. | Case | 1.5 | Not started | R8
23 | 2027-01-04 | 4 Travel kit | Spares kit defined and packed inside the case (REQ-M17) | Piezo modules, spare plate face, latches, fasteners. Fixed part of the packout. | Drop test | 1 | Not started | R8
24 | 2027-01-11 | 4 Travel kit | TIMED DRY RUN: teammate assembles from case, unaided (M7) | Under 10 minutes, first attempt, no instructions from you. Tests the design, not your memory. | Spares | 1.5 | Not started | R6
25 | 2027-01-18 | 4 Travel kit | Fix everything the dry run exposed | Second timed run passes. | Dry run | 3 | Not started | -
26 | 2027-01-25 | 4 Travel kit | Travel documentation: packout card, customs list, setup card | One page. Lives in the case. | Fixes | 1.5 | Not started | -
[5 empty] | TOTAL EFFORT (solo-days) | 82
[5 empty] | Available (26 wks x 2.5 days/wk, in-season) | 65
[5 empty] | Headroom (negative = overcommitted) | -17
Phase 1 alone is ~22 days and delivers the training tool that removes the robot dependency. Every later phase is independently useful.
If headroom is negative, the intended sacrifice order is: Phase 4 polish, then Phase 3 UI depth, then the rail. Phase 1 is never sacrificed.

## Dashboard
Dashboard
Formulas over the other tabs - updates as you edit Status.
PROGRESS
Total work items | 35
Done | 0
In progress | 0
Blocked | 0
% complete | 0%
EFFORT BY PHASE (solo-days)
Phase | Planned | Done | % done
1 Workshop target | 22.5 | 0 | 0%
2 Rail | 10 | 0 | 0%
3 Plates + UI | 28 | 0 | 0%
4 Travel kit | 21.5 | 0 | 0%
TOTAL | 82 | 0 | 0%
TRANSPORT CHECK (live from the Weight Budget and Packing tabs)
Projected packed weight (kg) | 18.5875
Airline limit (kg) | 23
Weight margin (kg) | 4.4125
Weight verdict | PASS with margin
Case linear sum (cm) | 158
Airline limit (cm) | 158
Size verdict | PASS
GATES
Gate | Week | Test | Action on failure
Adoption | 6 | Does a team member reach for it unprompted, and run it unaided? | Understand why not before adding rail, sensors or a suitcase to it
Plate gate | 10 | Prototype plate RMS <= 25 mm on held-out grid positions | Do not build four. Ship with stock plates + referee counting
Packing test | 20-21 | Full dry-run packout under 23 kg and 158 cm linear | Decide deliberately: oversize fee, freight, or workshop-only
Dry run | 24 | Teammate assembles from case, unaided, under 10 min | The design is ambiguous. Fix keying and labelling, re-run
Reliability tripwire | any | Two consecutive sessions needing tools to get running | Stop adding features. Everything here is downstream of it working

## Weight Budget
Weight Budget - the constraint that is discovered at the check-in desk
Blue = your input. Replace each estimate with an ACTUAL as parts get built and weighed. Size fails visibly; weight fails invisibly.
Subsystem | Item detail | Est. (kg) | Actual (kg) | Using (kg) | Flies? | Note
Motor | GM6020 - 468 g confirmed from manufacturer user guide | 0.47 |  | 0.47 | Yes
Head structure | Hub, 4 arms, plate carriers, balance masses | 1.8 |  | 1.8 | Yes
Armor plates | 4 x custom small-format plates with sensors bonded | 1.6 |  | 1.6 | Yes
Rotating electronics | Head MCU, front end, slip ring, wiring | 0.3 |  | 0.3 | Yes
Base electronics | Controller, universal-input 24V PSU, enclosure, E-stop | 1.5 |  | 1.5 | Yes
Travel stand | Legs, column, feet, latches - LARGEST UNCERTAINTY | 3.5 |  | 3.5 | Yes
Spares kit | Piezo modules, spare plate face, latches, fasteners | 0.8 |  | 0.8 | Yes
Case + foam | Shell, cut foam, corner protection - heavier than expected | 4.5 |  | 4.5 | Yes
Cables + PSU lead | Mains lead, DC leads, spare connectors | 0.4 |  | 0.4 | Yes
Workshop base | Ballasted steel pedestal - stays in Singapore | 12 |  | 12 | No
Rail assembly | Extrusion, carriage, belt, motor - stays in Singapore | 15 |  | 15 | No
| SUBTOTAL - items that fly |  |  | 14.87
| Contingency (% - appropriate before any part exists) |  | 25% | 3.7175
| PROJECTED PACKED WEIGHT | 18.5875
| Airline limit (kg) | 23
| Internal target (kg) - margin for a heavier case than planned | 20
| MARGIN vs. airline limit (kg) | 4.4125
| VERDICT | PASS with margin
The stand and the case are ~44% of flying mass and are the two least-defined items. Build and weigh both EARLY in Phase 4, not at the end.
Source: GM6020 mass from the RoboMaster GM6020 Brushless DC Motor User Guide. Every other figure is an estimate until an Actual is entered.

## Packing
Case Sizing + Packing Manifest
158 cm is a SUM of the three dimensions, not a length. Case shape is a free design variable - choose it AFTER the largest irreducible part is known.
CASE DIMENSIONS (external, cm)
Blue = your input. Set these once the part list is final.
Length |  | 85
Width |  | 45
Height |  | 28
LINEAR SUM (L+W+H) |  | 158
Airline limit |  | 158
Margin (cm) |  | 0
VERDICT |  | PASS
Longest internal member (cm, approx.) |  | 81
Internal diagonal (cm) |  | 93.9042
CASE SHAPE OPTIONS - all sum to ~158 cm
Shape (L x W x H, cm) | Sum | Longest member | Comment
70 x 48 x 40 | 158 | ~66 cm | Conventional suitcase proportions. Easy to handle, poor length.
85 x 45 x 28 | 158 | ~81 cm | Balanced. Current working assumption above.
105 x 32 x 20 | 157 | ~101 cm | Ski/golf-case proportions. Best length, awkward, more bending risk.
120 x 24 x 14 | 158 | ~116 cm | Extreme. Fragile as a case, hard to protect. Not recommended.
PACKING MANIFEST - one row per part. An empty foam pocket is a visible missing part.
Part | Qty | Longest dim (cm) | Mass each (kg) | Total (kg) | Foam pocket # | Packed?
Head hub with motor | 1 | 22 | 1.1 | 1.1 | P1 | No
Head arm + plate carrier | 4 | 20 | 0.18 | 0.72 | P2-P5 | No
Armor plate assembly | 4 | 15 | 0.4 | 1.6 | P6-P9 | No
Stand column section | 2 | 45 | 0.6 | 1.2 | P10-P11 | No
Stand leg | 3 | 50 | 0.55 | 1.65 | P12-P14 | No
Stand foot / ballast pocket | 3 | 12 | 0.1 | 0.3 | P15-P17 | No
Electronics enclosure | 1 | 25 | 1.5 | 1.5 | P18 | No
PSU + mains lead | 1 | 20 | 0.4 | 0.4 | P19 | No
Cable set | 1 | 15 | 0.2 | 0.2 | P20 | No
Spares kit box | 1 | 20 | 0.8 | 0.8 | P21 | No
Setup card + customs list | 1 | 30 | 0.05 | 0.05 | lid | No
|  |  | CONTENTS TOTAL (kg) | 9.52
|  |  | Longest part (cm) | 50
|  |  | Fits the case? | YES
|  |  | Items packed | 0 / 11
Part dimensions and masses are placeholders until real parts exist. Update them as you build - this tab is the single source of truth for the Dashboard transport check.

## BOM
Bill of Materials
Blue = your input. Phase column lets you stage funding: Phases 1-2 deliver the training tool, Phases 3-4 add measurement and portability.
Group | Item | Phase | Qty | Unit $ | Line $ | Own?
Head | GM6020 gimbal motor (468 g, 1.2 Nm, 18 mm hollow shaft) | 1 | 1 | 110 | 110 | Likely
Head | Hub + arm stock, plate carriers, balance masses | 1 | 1 | 80 | 80 | No
Head | Hardware: captive fasteners, latches, bearings | 1 | 1 | 20 | 20 | No
Workshop base | Steel plate, ballast, mounting hardware | 1 | 1 | 40 | 40 | Partly
Rail | Aluminium extrusion, 2.5-3 m | 2 | 1 | 90 | 90 | No
Rail | V-wheel carriage, GT belt, pulleys, idlers | 2 | 1 | 55 | 55 | No
Rail | Drive motor + limit switches | 2 | 1 | 45 | 45 | Maybe
Plates | 4 x plate substrate + replaceable impact faces | 3 | 4 | 22 | 88 | No
Plates | Piezo elements | 3 | 16 | 1.5 | 24 | No
Plates | Analogue front end: comparators, op-amps, PCB | 3 | 4 | 9.5 | 38 | No
Rotating elec. | Head MCU board | 3 | 1 | 20 | 20 | No
Rotating elec. | Slip ring capsule, hollow-shaft compatible | 3 | 1 | 35 | 35 | No
Rotating elec. | Connectors, wiring, strain relief | 3 | 1 | 25 | 25 | No
Base elec. | Base controller board | 1 | 1 | 30 | 30 | Maybe
Base elec. | Universal-input 24 V PSU (100-240 V) | 1 | 1 | 45 | 45 | No
Base elec. | Enclosure, hardware E-stop, wiring | 1 | 1 | 35 | 35 | No
Travel stand | Extrusion or tube stock, feet, ballast pockets | 4 | 1 | 60 | 60 | No
Travel stand | Draw latches, cam locks, captive hardware | 4 | 1 | 40 | 40 | No
Case | Case shell | 4 | 1 | 55 | 55 | No
Case | Custom-cut foam, corner protection | 4 | 1 | 35 | 35 | No
Spares | Piezo modules, spare plate face, latches, fasteners | 4 | 1 | 50 | 50 | No
|  |  |  | SUBTOTAL (all phases) | 1020
|  |  |  | Less items likely already owned | 110
|  |  |  | LIKELY SPEND | 910
|  |  |  | Phase 1 (workshop target) | 360
|  |  |  | Phase 2 (rail) | 190
|  |  |  | Phase 3 (plates + electronics) | 230
|  |  |  | Phase 4 (travel kit) | 240
|  |  |  | Phases 1-2 only (the training tool) | 550
|  |  |  | Phases 3-4 (measurement + portability) | 470
Staging option: fund Phases 1-2 now ($550, the training tool), decide Phases 3-4 at the Week 8 review - which also defers plate spend past the Week 10 gate.

## Risks
Risk Register
Score = Impact x Likelihood (1-5 each). Blue = your scoring inputs. Review at every gate.
ID | Risk | Imp | Lik | Score | Severity | Mitigation | Review at
R1 | Slotted joints loosen under vibration and repeated impact | 5 | 4 | 20 | Critical | REQ-M9: separate locating from clamping in every joint. Endurance run and full joint re-check in Phase 1, not Phase 4. | Wk 5
R2 | Only the builder can operate or fix it | 5 | 4 | 20 | Critical | M2 makes this a tested requirement, not an aspiration. Keying, labelling, self-test and a setup card in the case. A teammate runs Phase 1 acceptance. | Wk 6
R3 | Weight creep pushes the packed kit past 23 kg | 4 | 4 | 16 | Critical | Weigh every part as it is made. Stand and case are 44% of flying mass and least defined - build and weigh them EARLY in Phase 4. | Wk 20
R4 | Piezo bonds fatigue and silently corrupt localisation | 4 | 4 | 16 | Critical | REQ-E6 per-channel drift detection; field-replaceable modules; boot self-test on the Health screen. | Wk 10
R5 | Solo builder, in-season workload, project stalls part-built | 4 | 4 | 16 | Critical | Phase 1 delivers standalone value in 6 weeks; every later phase is independently useful. Stopping at any phase is acceptable. | Wk 6
R6 | Travel stand cannot be both packable and stable enough | 4 | 3 | 12 | High | Contained by the architecture - workshop use is unaffected. Ballast filled on site rather than chasing stiffness in the suitcase. | Wk 18
R7 | No usable mains power at the competition venue | 4 | 3 | 12 | High | Dual DC input accepting a borrowed RM pack. No battery can be flown regardless. Confirm venue power (Q3). | Wk 8
R8 | Case fails baggage handling; parts arrive damaged | 4 | 3 | 12 | High | Drop test before travelling. Spares kit inside the case. Irreplaceable electronics in hand luggage. | Wk 22
R9 | GM6020 torque marginal once the head is fully built | 3 | 3 | 9 | High | Budget head inertia before building. Keep plate radius small - inertia scales with r^2, the cheapest lever available. | Wk 4
R10 | Injury from the spinning head or projectiles | 5 | 2 | 10 | High | Hardware E-stop cutting motor power directly. Balance verification before first full-speed run. Captive fasteners. Eye protection. | Wk 4
R11 | Slip ring wears or becomes intermittent | 3 | 3 | 9 | High | REQ-E1 keeps only power and digital across the interface. REQ-E3 keeps a wireless data path open as a fallback. | Wk 11
R12 | Referee gear unusable on a non-robot fixture at a venue | 2 | 3 | 6 | Medium | Custom plates work standalone, so referee is a workshop cross-check not a dependency. Confirm the rules position (Q4). | Wk 8
| Highest score: |  |  | 20
Thresholds: Critical >=15, High >=9, Medium >=4, Low <4.

## Metrics
Success Metrics
Blue = fill in as measurements land.
ID | Metric | Target | Actual | Due | Status | Why it is the right measure
M1 | Setup time, case to first shot | <= 10 min, one person, no tools |  | Wk 24 | Pending | Decides whether it actually gets used
M2 | Use by someone who did not build it | Team member runs a full session unaided, first attempt |  | Wk 6 | Pending | The primary user test. Tests the design, not the builder's memory
M3 | Sessions between tool-requiring failures | >= 20 |  | ongoing | Pending | Encodes 'switch it on and start using it'
M4 | Packed size | <= 158 cm linear, case included |  | Wk 21 | Pending | Binary pass/fail at the check-in desk
M5 | Packed weight | <= 23 kg, target <= 20 kg |  | Wk 21 | Pending | 3 kg margin absorbs spares and a heavier case
M6 | Spin speed consistency | <= 2% from commanded, 0.25-3.0 rev/s |  | Wk 4 | Pending | Two sessions a week apart must be comparable
M7 | Hit localisation accuracy | <= 25 mm RMS, >= 95% quadrant |  | Wk 17 | Pending | Honest limit for piezo TDOA on a small plate
M8 | Adoption | >= 8 team sessions in the first month, by >= 2 different people |  | Wk 10 | Pending | A tool one person uses is a rig; a tool the team uses is equipment
M2 and M8 are the pair that matter. Every other metric can be satisfied by a machine only its builder can operate.

## Open Questions
Open Questions
Q1 and Q7 gate Week 1-2. Q1 can reorder the whole back half of the plan.
ID | Question | Blocks | Needed by | Status | Answer
Q1 | Which competition and date is the travel deadline? RMUL 2026 mainland sites ran Mar-May 2026, so this plan assumes the 2027 cycle (~Mar 2027). If the real date is earlier, Phase 4 must move ahead of Phase 3. | All Phase 4 scheduling | Wk 2 | Open
Q7 | Do you have 3D printing and machining access, or is everything cut by hand? | Realistic effort for every mechanical part | Wk 1 | Open
Q6 | What plate height above the floor matches the robots you most need to practise against? | Stand height, therefore packed length | Wk 3 | Open
Q2 | Is the ~$830 budget approvable, or should it be staged at the Week 8 review? | Phase 3 and 4 procurement | Wk 4 | Open
Q5 | How long is the workshop rail, and what mounting does the space allow? | Phase 2 rail design | Wk 5 | Open
Q3 | Is mains power available near a usable test area in a competition pit? | Power architecture and on-site fallback | Wk 8 | Open
Q4 | Can referee gear be used on a non-robot fixture at a venue, and is a spare set available? | Whether referee cross-check extends beyond the workshop | Wk 8 | Open